# MEETING MINUTES

Meridian Valley Foundation, Spring Donor Reception Planning

| Date | Tuesday, March 3, 2026 |
| --- | --- |
| Time | 10:00 AM to 10:05 AM |
| Location | Zoom |
| Participants | Dana Whitcombe, Priya Ramanathan, Marcus Oyelaran, Jordan Lee |

# Executive Summary

The team settled the plan for the spring donor reception on Thursday, April 23, from 6:00 to 8:30 PM at Castellane Gallery, for up to 160 guests. Dana approved the venue contract and chose Lumenhall Catering. The projected cost is about $14,720, under the $15,000 approved budget. The venue hold expires April 10, so the contract will be signed this week.

# Guest List

The list stands at 140 names: major donors, the board, and the 12 new monthly givers from the fall campaign. Priya proposed a cap of 160 so the room does not feel crowded, and Dana agreed.

Still missing: corporate sponsors, pending two contact lists.

Final list due to Jordan on Friday, March 13.

# Venue

Castellane Gallery is holding Thursday, April 23, 6:00 to 8:30 PM. The rental is $4,200 for the evening, including gallery staff for setup and teardown, with half due as a deposit on signing.

The hold expires April 10. Dana approved signing.

Jordan will route the contract to Dana and has scheduled the signature for Thursday, March 5.

# Catering

Two quotes were compared. Lumenhall Catering quoted $62 per guest for heavy appetizers and a wine bar; the other caterer quoted $71 and could not provide a wine bar. Priya noted that Lumenhall catered last year's board dinner and was well received. Dana chose Lumenhall.

Marcus will confirm the menu, including vegetarian and gluten-free options.

Final headcount is due to the caterer on April 9.

# Program

Dana will give a five-minute welcome. A scholarship student from the arts scholarship cohort will speak for three minutes; Priya will confirm her this week (name to be confirmed). There will be no live auction: Dana wants the evening to read as a thank-you, not an ask. Pledge cards will be on the tables.

# Invitations

Jordan will reuse last year's design. Email invitations go out Monday, March 16, and printed invitations go to the mail house the same day. RSVPs close April 2.

# Budget

Projected cost

| Item | Amount |
| --- | --- |
| Venue rental | $4,200 |
| Catering, 160 guests at $62 | $9,920 |
| Printing | $600 |
| Total | $14,720 |

# Action Items

| Owner | Action | Deadline |
| --- | --- | --- |
| Priya Ramanathan | Send the final guest list to Jordan | Friday, March 13 |
| Marcus Oyelaran | Send the venue contract to Jordan for routing | Before Thursday, March 5 |
| Jordan Lee | Route the venue contract to Dana for signature | Thursday, March 5 |
| Marcus Oyelaran | Confirm the menu and dietary options with Lumenhall Catering | TBD |
| Priya Ramanathan | Confirm the student speaker and her name | This week |
| Jordan Lee | Send email invitations and deliver printed invitations to the mail house | Monday, March 16 |
| Marcus Oyelaran | Give the caterer the final headcount | Thursday, April 9 |

Prepared by Jordan Lee, Executive Assistant, March 3, 2026